## Slide 1
PROGRESS UPDATE · SEPTEMBER 2026
VR Hydrology
Digital Twin
From streamflow model to Meta Quest 3S — a full status review and the plan ahead
Prepared for Saurabh Kulkarni

## Slide 2
AGENDA
What This Covers
01
What's Been Built
Project vision, recap
The target data-to-headset pipeline
Documentation & live data pipeline
Unity project scaffold
Delivery status & open items
02
What's Next
The 12-week build roadmap
Immediate next steps
VR HYDROLOGY DIGITAL TWIN
02

## Slide 3
PART ONE · WHAT'S BEEN BUILT
Project Vision
Turning the lab's streamflow forecasting model into an immersive VR digital twin
3D
Walk the Watershed
Terrain, river network, and gauge stations in 3D — not flat charts on a screen.
ML
Live Forecasts
Tap a station, pull up streamflow forecasts with uncertainty bounds, on the spot.
VR
Stronger Stakeholder Demos
Sponsors and collaborators put on the Quest 3S and experience the model directly, no PC required.
VR HYDROLOGY DIGITAL TWIN
03

## Slide 4
PART ONE · WHAT'S BEEN BUILT
How Data Becomes a VR Experience
1
Data Sources
USGS discharge (Aug 11 – Sep 8, 2026) + NWS climate snapshot (as of Sep 9, 2026) — pulled live by this project's own pipeline, not just assumed to exist.
2
Preprocessing
Cleaning and formatting in Python — already exists.
3
ML Forecast Model
Streamflow forecast + uncertainty bounds — already exists.
4
Export Layer
CSV → JSON, built and verified in this project (data-pipeline/).
5
Unity Application
Terrain, data, UI, model logic — scaffold built; scene assembly is Editor work.
6
Meta Quest 3S
Deployed VR digital twin — the end goal.
Teal marker = already exists or built in this project Grey marker = built in the Unity Editor (not yet started)
04

## Slide 5
PART ONE · WHAT'S BEEN BUILT
Documentation & Data Pipeline
DOC
Full phase-by-phase documentation
14 files covering all 10 build phases, the 12-week pacing plan, pitfalls, and the resource library.
PY
Live data pipeline — Phase 5
fetch_live_data.py pulls real USGS discharge + climate on any date interval you pass it; export_station_json.py packages it into a JSON bundle with explicit start/end dates, plus a CSV export.
3
stations, live
2
public APIs
0
API keys needed
Discharge history: Aug 11 – Sep 8, 2026 (29 days) · Climate snapshot: Sep 9, 2026 · Forecast: Sep 9 – Sep 15, 2026
station JSON — real live values
pulled Aug 11 – Sep 9, 2026
{
"stationId": "USGS-08057000",
"name": "Trinity Rv at Dallas, TX",
"latitude": 32.7748517,
"longitude": -96.8219464,
"period": { "start": "2026-08-11",
"end": "2026-09-08" },
"readings": [
{ "date": "2026-08-11", "dischargeCfs": 437.0 },
... 29 daily readings ...
{ "date": "2026-09-08", "dischargeCfs": 421.0 }
],
"climate": { "avgTempC": 29.0, "avgPrecipMm": 0.0,
"asOfDate": "2026-09-09" },
"soil": { "type": "sandy loam",
"infiltrationRateMmHr": 3.6 },
"forecastPeriod": { "start": "2026-09-09",
"end": "2026-09-15" },
"forecast": [
{ "date": "2026-09-09", "dischargeCfs": 421.0,
"lowerBound": 389.4, "upperBound": 452.6 }
]
}
VR HYDROLOGY DIGITAL TWIN
05

## Slide 6
PART ONE · WHAT'S BEEN BUILT
Unity Project Scaffold
Script | Role
StationDatabase.cs | Single source of truth (ScriptableObject)
StationDataLoader.cs | Loads station JSON at runtime
StationData.cs | Typed models matching the JSON schema
StationMarker.cs | Gauge-station prefab, opens its panel
StationPanelController.cs | World-space UI: reading & forecast
LayerToggleController.cs | Soil / climate / river overlay toggles
RiverNetworkRenderer.cs | Starting point for river reaches
Design principle
One ScriptableObject (StationDatabase) holds every station's data.
Every other script reads from it — nothing duplicates the data.
Terrain, UI, and model scripts stay decoupled: swapping a dataset or model shouldn't touch the terrain code.
sample_data/ now ships a real live snapshot (USGS + NWS) — generate_sample_data.py still covers fully offline iteration.
VR HYDROLOGY DIGITAL TWIN
06

## Slide 7
PART ONE · WHAT'S BEEN BUILT
Delivery Status
Item | Status | Note
Live data pipeline | DELIVERED | Real USGS discharge (Aug 11 – Sep 8, 2026) + NWS climate (as of Sep 9, 2026) now power sample_data/
Project scaffold (.zip) | DELIVERED | 70+ files: docs/, data-pipeline/, unity-project/
Project report (.docx) | DELIVERED | Build summary, structure, and next steps
This progress deck (.pptx) | DELIVERED | You're looking at it
GitHub repository push | PENDING | Connected GitHub App can't create new repos (403, retried) — needs an empty repo to push into
To close this out:
Create an empty repository at github.com/new (no README/gitignore/license) and share its name — everything gets pushed over in one commit, or push it yourself with the git commands in the project report.
VR HYDROLOGY DIGITAL TWIN
07

## Slide 8
PART TWO
What's Next
The 12-week build roadmap, and what to start this week

## Slide 9
PART TWO · WHAT'S NEXT
12-Week Roadmap
1
WKS 1–2
Foundations & Setup
Unity + Meta XR SDK, Developer Mode.
2
WKS 3–4
First VR Scene
Build & deploy “Hello World”.
3
WKS 5–6
Terrain & River Network
Terrain, reaches, station markers.
4
WKS 7–8
Real Data Integration
Discharge & climate now live — soil + real ML forecast next.
5
WKS 9–10
Dashboards & Model
Charts, panels, precomputed forecasts.
6
WKS 11–12
Assembly & Deploy
Full scene, perf pass, ship it.
VR HYDROLOGY DIGITAL TWIN
09

## Slide 10
Immediate Next Steps
Start this week
1
Create the GitHub repo & push
Create an empty repo and share the name — everything gets pushed over immediately.
2
Install Unity + Meta XR Core SDK
Unity 6000.0.66f2+, Android Build Support, Developer Mode on the Quest 3S.
3
Complete the “Hello World” tutorial
Confirms the full toolchain and headset connection work end to end.
4
Finish real-data integration
Discharge & climate are live now (USGS + NWS) — soil and the real forecast model are what's left.
Questions along the way? Bring them to the weekly check-in — don't stay stuck alone.